HEA Baselines Training
24th to 30th October 2016
Badplaas, Mpumalanga, South Africa
### Report to:
### South African Vulnerability Assessment Committee, Directorate: Subsistence Farming, Department of Agriculture, Forestry and Fisheries and the
### Regional Vulnerability Assessment and Analysis Programme, Food, Agriculture and Natural Resources Directorate, SADC

Charles Rethman, November 2016

### Activities Summary
The Baselines Training for the SAVAC / MpumaVAC / LimVAC consisted of the following activities:
1. Preparing and customising the training materials. Done on 10th–14th October 2016.
2. The delivery of the training itself, including one day with a field visit to explore the actual implementation of what was being learnt. Completed on 24st –30th October 2016.
3. Customising and printing of materials for use by the teams in their field work. Done on 13th–14th October 2016.
### Preparation
Completed in Pretoria.
The consultant handed over all the materials for printing, except those that required customising and adjusting for conditions in Mpumalanga and Limpopo. The consultant also prepared an Agenda or Programme for the training.
The HEA Practitioners' Field Handbook, in particular, needed amending again for local conditions. Units of measurement had to realistically reflect those in use in the local context (e.g. a 'bag' of grain is 50 kg) and recent local examples (e.g. of the seasonal calendar) had to be included. Aspects such as local names and variants were also included. The energy values in the booklet had to be listed in kilojoules, not kilocalories (and the threshold for the average human requirement set at 8800 kJ).
The programme was developed and discussed with the SAVAC Secretariat. Agreement was reached on Tuesday 18th October and the drafts were handed over for printing. The files containing the session notes, presentations and handouts with exercises that were to be printed for participants have been made into a single document, which can be printed at a go and removes the need for collating, which is an onerous and time-consuming task. The Department did its own printing and the materials were of reasonably good quality. Printing nevertheless still takes two full working days to complete.
### Delivery of the Training
The training itself did not start well, as collating and filing of all the materials ended up using a whole day (Saturday 31st October). The team did attempt to file the papers on Friday the night before, but a power cut halted the process. Collating and filing may seem a simple process but for this large volume of material and the numbers of participants it was very time-consuming. The consultant had previously warned the team of the length of time it took to prepare materials for training and that adequate time had to be allocated for the task. With hindsight, a faster way of completing this task would have been to have filed the documents as they got printed—this would have saved much time on sorting and organising. Hence, at the office where the printing was taking place, the a bunch of notes should have been added to each file as they just when the printing of it was completed, keeping the reverse sequence under which the documents are organised electronically. (i.e. starting at the last document, print and then immediately place each copy in its file, adding each document as it comes hot off the printer).
However, the training did start on Sunday 1st November and kicked off very well. The participants were asked to write down their Expectations and Fears, which were logged and kept for this report. The majority of participants (52%) expected that they would learn and understand HEA, including its methodological issues and details. A smaller number expected to be able to apply this newly-learnt knowledge in the field directly—a higher expectation but not an unreasonable one since they would all be going to the field to implement almost directly afterwards.
The greatest number of people feared that the training programme would not be finished or that it would rushed through in order to get finished. Others feared that the content would be difficult to understand. The remainder had a variety of concerns, many of which were about the field work itself and not necessarily the training.
Training for baselines assessment has to cover three important aspects of the work that is being trained for:
1. Participants need to learn how carry out their interviews with people in order to to undertake the work;
2. Participants need to clearly understand all the underlying concepts with HEA, especially regarding the calculations and meanings of the results
3. Participants need to remember key elements of the approach, as they must not leave out any essential work in the field.
The trainer therefore tried to balance the delivery to allow enough time and to include enough examples that covered the first two aspects above, with enough revision to ensure the third.
At the end of the training the participants were asked to complete evaluation questionnaires, the summary of which is as follows:
Table 1 - Evaluation summary
Item	Question	Ranking
		Strongly Agree	Agree	Neutral	Disagree	Strongly Disagree
1	My main expectations of the workshop were achieved	31.0%	62.1%	3.4%	-	3.4%
2	What I have learned in this workshop will help me in my work	60.7%	35.7%	3.6%	-	-
3	The objectives of this workshop were relevant to me and were achieved	35.7%	60.7%	3.6%	-	-
Item	Question	Very Good	Good	Average	Bad	Very Bad
4	What do you think of the pre-workshop preparation and planning?	10.3%	58.6%	24.1%	6.9%	-
5	What did you you think about the format of the workshop?	20.7%	58.6%	20.7%	-	-
6	What did you think of the support provided for the workshop?	44.8%	41.4%	13.8%	-	-
7	What did you think of the venue?	13.8%	31.0%	34.5%	17.2%	3.4%
8	What did you think about the food?	7.1%	39.3%	35.7%	14.3%	3.6%
9	What did you think of the practical arrangements?	10.7%	21.4%	53.6%	7.1%	7.1%

The participants' comments on the first three questions included the statement that the training could be used in a large variety of applications, such as natural resource management or other poverty reduction programmes. A few participants expressed that there were a lot of concepts to grasp in such a short time.
Participants found different things interesting in the course, the response was quite spread out. However, the Wealth Breakdowns and Calculations were somewhat more preferred. As for the least interesting section, the greatest number said None (although many respondents also did not answer this question—and this may have been “none” to them too) and a few mentioned the field exercise.
An important output from the training was also a list of typical expense items that it was expected would be found among village households. This list will form the basis of the Resilience line and other Poverty lines or thresholds in the analysis in future.
Overall, the participants from the ZVAC were interested, enthusiastic and they conducted themselves professionally. The workshop included active work on two Saturdays and one Sunday but participants remained alert and active.

Table 2 - What participants found and did not find interesting
Most interesting		Least Interesting
All	7.1%	Sorting the material on the first day	14.3%
All, except for the field visit practical	3.6%	Calculations	7.1%
Exercises	10.7%	Field visit practical	21.4%
Background on HEA	3.6%	Exercises	7.1%
Herd dynamics	3.6%	Theory (introductory sessions)	7.1%
Presentations, group work and calculations	10.7%	Presentations	7.1%
Wealth breakdowns, calculations	28.6%	None	35.7%
Mock interviews	3.6%
Organisation of the field tools	3.6%
Field visit practical	14.3%
Analysis of the data after the field exercise	3.6%
Baseline spreadsheet	3.6%
Analysis	3.6%

### Customisations and Preparations for the Field after the Training
During the workshop, comments were received about the Field Interview Forms and the Field Practitioners' Handbook. These comments were used after the workshop to prepare revised versions of these documents that would better reflect the Zambian situation and norms. These were shared with the DMMU for printing.
The changes included new population distributions (that are based on the most recent census) and other changes.
The consultant met with Mr Teddy Kabunda of Oxfam and discussed the process of the work.
The consultant also met briefly, though not formally, with Mr Partrick Kangwa, the National Coordinator for the DMMU, while working with the DMMU team. Mr Lusajo Ambukege, the Systems Analyst and GIS Office in the DMMU, shared the livelihood zone shape files, which will enable important the consultant to calculate populations and other important information from national data sets for the Baselines Analysis.
Finally, the consultant constructed a revised blank Baseline Storage Spreadsheet, customised for Zambia. This has been made available to the field teams for their assessment work.
Departed Lusaka on 11 November 2015 at 13:00.

Charles Rethman
November, 2015.